## Sheet1
Sprint | Business | Design | Tech | Film
1: Feb 20 | Research nutrition info (total calories, protein, carbs, sugars) | 3some, 2some, single blocks, look like a chalk drawing/playful, grey/black background with texture | Either randomly generate platforms or loop long visual image of platforms, slow down scrolling of game play if calories are below 1300 or above 1800 | Sound file for food consumption, different sound for “good” vs “bad” food
|  | pick font, create colored square that it is in, count down from 60 seconds | Make the clock countdown, make numbers turn red for final 3 second countdown | Sound file for going below 1300 or above 1800 calories (alert sound)
2: March 6 | Update planning as project develops and changes | Compile food (ask tech for size/type) | Randomly generate food, assign numbers to each food, create database for each play that totals number of calories, carbs, protein, sugar | Sound file for 3,2,1 countdown
|  | Create simple box with numbers 1300-1800 greyed out, choosing font type | Must be able to calculate assigned numbers per image (will show up in end nutrition screen, and in calorie counter box) | Sound file for hitting the buttons
|  | Create overlay screen with platform greyed-out, retry button, exit button (both within some kind of square) | Make the retry and exit buttons work | Sound file for background noise/music that is 60 second in length
3: March 20 | Survey on character (boy/girl or animal/character) | boy and girl character, illustrate character in 5-7 positions so that it looks like they are moving |  | Use sound file from the rest of the game for high score board
| create facebook page/create marketing plan using logo | design logo, large/small
Have test group try the beta version of application
4: April 3 | Research if a high score board is motivating | Create overlay screen with platforms greyed-out, list of players and their scores | Come up with a way to tally scores and make them appear in high score board | Sound file for when screen pops up
| Research if the McDonald’s nutrition label is a good simplified version | Create overlay screen with platforms greyed-out, create table with simplified nutrition information including: calories, carbs, proteins, sugar | Take the information from the character’s food intake and make that numerically show up in chart
Take the application to an elementary school class for further feedback
5: April 17 | Research first name, last name, email, Facebook (what should be used?) | Create overlay screen with platforms greyed-out, have area where student can type in name | Create the ability to type a name in and retain the information in a database for Cerner data collection | Sound file while login screen is up to motivate person to type (active sound)
|  | Create flash animation of chalk drawing the platforms slowly | Create a loading screen | Different music to imply something is happening/that player is waiting and being entertained